## Sheet1
Task	Expected Completion Date	Actual Completion Date	Reason for Delay
Submit Topic Proposal	02/09/20	04/06/20	Topic Proposal did not meet parameters for validity nor was the topic appropriate for the goal of the project
Requirements	03/31/20	04/06/20	Project Design and Function were up in the air. Risk of flopping to another project almost altogether.
Use Case	03/31/20	04/06/20	“^”
Brainstorm Website Design	03/14/20	03/14/20
SPMP Initialization	03/20/20	03/20/20
Solidify Domain Name	04/06/20	04/18/20	Domain changed from Inside-Infosec.com to fromwire2hire.net
Solidify Hosting Candidate (AWS)	03/26/20	03/26/20
Acquire Host	04/01/20	04/28/20	Had to remake host due to unforseen display error
Acquire Domain Name Registration	04/08/20	04/20/20	Back and forth on what the name of the site should be. Decided on “fromwire2hire”
Design Review	03/21/20	04/08/20	Preperation of the documents and final design plan took longer then expected due to multiple controllable and uncontrollable factors.
Initiate Wordpress Site	04/10/20	04/28/20	Had to remake host system after display error
Initialize Home Page	04/28/20	04/28/20
Complete Home Page	04/30/20	04/30/20
Initialize Resume Page	04/28/20	04/28/20
Complete Resume Page	04/29/20	04/29/20
Initialize Portfolio Page	04/30/20	04/30/20
Complete Portfolio Page	04/26/20	04/26/20
Complete Deliverable Documents	05/01/20	05/01/20
Finalize Prototype of Site	04/29/20	04/29/20
Finalize Presentation	05/01/20	05/01/20
Client Review and Feedback	Ongoing	Ongoing		s