## Gantt Chart
GANTT CHART
PROJECT TITLE |  | FromWire2Hire |  |  |  | COMPANY NAME | [6 empty] | Towson University
PROJECT MANAGER |  | Josh Robertson |  |  |  | DATE | [6 empty] | 2020-05-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Propose and Discuss Topic | Josh | 2020-02-15 | 2020-05-01 | 100% | bar: WEEK 1 F to WEEK 6 F; WEEK 8 M to WEEK 8 F
1.1.1 | Requirements Discussion | Josh | 2020-04-08 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 6 F; WEEK 8 M to WEEK 8 F
1.2 | Tools Discussion and Brainstorm | Josh | 2020-04-08 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 7 W; WEEK 8 M to WEEK 8 F
1.3 | Conceptualize Design and Function | Josh | 2020-03-18 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 6 T; WEEK 8 M to WEEK 8 F
1.4 | Budget | Josh | 2020-02-19 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 4 M; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F
1.5 | Design Review Meeting | Josh | 2020-04-08 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 6 R to WEEK 8 F
1.6 | Risk Management | Josh | 2020-02-21 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 8 F; WEEK 9 T to WEEK 11 F
2 | Project Definition and Planning
2.1 | Hosting Service Chosen | Josh | 2020-03-24 | 2020-05-01 | 100% | bar: WEEK 4 M to WEEK 5 F; WEEK 8 M to WEEK 8 F
2.2 | Github Repo Established | Josh | 2020-03-29 | 2020-05-01 | 100% | bar: WEEK 3 F to WEEK 4 T; WEEK 4 F to WEEK 5 F; WEEK 8 M to WEEK 9 T
2.3 | Website Name and Branding | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 3 F to WEEK 4 R; WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 10 M
2.4 | SPMP Initialization | Josh | 2020-04-01 | 2020-05-01 | 100% | bar: WEEK 3 F to WEEK 12 F
3 | Structural Solidification
3.1 | Website Initiation | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 4 W to WEEK 5 F; WEEK 7 M to WEEK 8 F; WEEK 9 R to WEEK 11 F
3.2 | Individual Page Development | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 7 T to WEEK 12 T
3.2.1 | Individual Page Completion | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 4 W to WEEK 5 F; WEEK 7 M to WEEK 8 F; WEEK 11 M to WEEK 12 F
3.2.2 | Domain Registration | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F; WEEK 9 R to WEEK 12 F
3.3 | Test and Demo Planning | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 8 M to WEEK 8 F
3.3.1 | Plugin Research for Functionality | Josh | 2020-04-18 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 6 T to WEEK 10 T
4 | Project Performance / Monitoring
4.1 | Project Objectives | Josh | 2020-02-15 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 5 F; WEEK 6 F to WEEK 8 F; WEEK 11 M to WEEK 12 F
4.2 | Quality Deliverables | Josh | 2020-03-24 | 2020-05-01 | 100% | bar: WEEK 5 M to WEEK 5 F; WEEK 6 F to WEEK 8 F; WEEK 11 M to WEEK 12 F
4.3 | Effort and Cost Tracking | Josh | 2020-02-15 | 2020-05-01 | 100% | bar: WEEK 2 M to WEEK 11 F
4.4 | Project Performance | Josh | 2020-02-15 | 2020-05-01 | 100%